## RACI Matrix
Activity | Project Manager | Solution Architect | Lead Developer | Frontend Developer | QA Manager | Business Analyst | DevOps Engineer | Stakeholders
Project Charter Development | A | C | I | I | I | C | I | R
Stakeholder Analysis | A | I | I | I | I | R | I | C
Requirements Gathering | R | C | I | I | I | A | I | C
Requirements Validation | C | R | I | I | I | A | I | C
Architecture Design | C | A | R | I | I | I | C | I
Database Design | I | C | I | I | I | I | A | I
UI/UX Design | C | I | I | A | I | R | I | C
Backend Development | C | C | A | I | I | I | I | I
Frontend Development | C | I | I | A | I | I | I | I
Database Implementation | I | C | I | I | I | I | A | I
API Integration | C | C | R | C | I | I | C | I
Unit Testing | I | I | R | R | C | I | I | I
Integration Testing | C | I | C | I | A | I | C | I
Performance Testing | I | C | C | I | A | I | C | I
User Acceptance Testing | R | I | I | I | C | A | I | C
Security Audit | C | C | I | I | I | I | A | I
Environment Setup | C | I | I | I | I | I | A | I
Data Migration | C | C | I | I | I | I | A | I
Deployment Planning | A | C | C | I | C | I | R | I
Go-Live Execution | A | C | C | I | C | I | R | I
User Training | C | I | I | I | I | A | I | R
Post-Deployment Support | R | C | C | I | C | I | C | C
Project Closure | A | I | I | I | I | I | I | C

## RACI Legend
RACI MATRIX LEGEND & GUIDELINES
Code | Role | Description
R | Responsible | Person who does the work to complete the task
A | Accountable | Person ultimately answerable for correct completion (only one A per task)
C | Consulted | People whose opinions are sought (two-way communication)
I | Informed | People who are kept up-to-date on progress (one-way communication)
BEST PRACTICES
Rule | Guideline | Rationale
One Accountable | Each task must have exactly ONE person accountable | Ensures clear decision authority
Multiple Responsible | Tasks can have multiple people responsible | Distributes workload effectively
Limit Consulted | Avoid having too many people consulted | Prevents decision paralysis
Information Flow | Keep informed parties updated proactively | Maintains stakeholder satisfaction
Clear Roles | No person should be both R and A for same task | Prevents conflict of interest