## Executive Summary
PROJECT STATUS DASHBOARD
Report Date: March 03, 2026
KEY PERFORMANCE INDICATORS
Metric | Current Value | Target | Status
Overall Progress | 45% | 100% | On Track
Budget Utilization | $175K / $250K | $250K | Under Budget
Schedule Performance | Week 8 / 12 | Week 12 | On Track
Active Risks | 6 High Priority | < 3 High | At Risk
Team Utilization | 85% Average | 80-90% | Optimal
Milestone Completion | 15 / 30 | 30 | On Track
Stakeholder Satisfaction | 8.2 / 10 | > 8.0 | Good
Quality Score | 92% | > 90% | Excellent
PROJECT HEALTH SUMMARY
Area | Status | RAG | Notes
Scope | Stable | 🟢 | No scope changes in last 2 weeks
Schedule | On Track | 🟢 | All milestones met to date
Budget | Under | 🟢 | $5K under budget with $75K remaining
Quality | Good | 🟢 | Defect rate within acceptable range
Resources | Adequate | 🟢 | Team fully staffed
Risks | Manageable | 🟡 | 6 active risks being monitored
Stakeholders | Engaged | 🟢 | Weekly steering committee meetings

## Milestones
MILESTONE TRACKER
Phase | Milestone | Planned Date | Actual Date | Status | Notes
Planning | Project Charter Approved | 2024-01-17 | 2024-01-17 | Complete | Approved by steering committee
Planning | Stakeholder Analysis Complete | 2024-01-26 | 2024-01-26 | Complete | 25 key stakeholders identified
Requirements | Requirements Documented | 2024-02-16 | 2024-02-16 | Complete | 120 requirements approved
Design | Architecture Defined | 2024-02-26 | 2024-02-26 | Complete | Cloud-native microservices
Design | Database Schema Approved | 2024-03-05 | 2024-03-05 | Complete | PostgreSQL with Redis
Design | UI/UX Mockups Complete | 2024-03-14 | 2024-03-12 | Complete | Delivered 2 days early
Development | Backend API Complete | 2024-04-02 |  | In Progress | 60% complete - on track
Development | Frontend Components Built | 2024-04-05 |  | In Progress | 40% complete
Development | Integration Complete | 2024-04-16 |  | Not Started | Planned for April
Testing | QA Testing Complete | 2024-05-03 |  | Not Started
Testing | UAT Sign-off | 2024-05-25 |  | Not Started | 20 pilot users identified
Deployment | Production Ready | 2024-06-03 |  | Not Started | Blue-green deployment planned
Deployment | Go-Live | 2024-06-03 |  | Not Started | War room scheduled

## Budget Tracking
BUDGET TRACKING & FORECAST
Phase | Budgeted Amount | Actual Spent | Remaining | Variance | Status
Planning | $25,000 | $25,000 | $0 | $0 | Complete
Requirements | $35,000 | $35,000 | $0 | $0 | Complete
Design | $50,000 | $48,000 | $2,000 | +$2,000 | Complete
Development | $100,000 | $67,000 | $33,000 | TBD | In Progress
Testing | $25,000 | $0 | $25,000 | TBD | Not Started
Deployment | $15,000 | $0 | $15,000 | TBD | Not Started
TOTAL | $250,000 | $175,000 | $75,000 | +$2,000 | Under Budget

## Resource Allocation
RESOURCE ALLOCATION & UTILIZATION
Role | Allocated % | Current Utilization % | Status | Notes
Project Manager | 50% | 92% | Over Allocated | Managing scope changes
Solution Architect | 40% | 85% | Optimal | Design phase complete
Lead Developer | 100% | 105% | Over Allocated | Sprint crunch time
Frontend Developer | 100% | 98% | Optimal | On schedule
Backend Developer | 100% | 102% | Optimal | API development
QA Manager | 60% | 45% | Under Utilized | Ramping up for testing
Business Analyst | 80% | 75% | Optimal | UAT planning
DevOps Engineer | 30% | 110% | Over Allocated | Infrastructure setup