## Risk Register
Risk ID | Category | Risk Description | Impact | Probability | Risk Score | Severity | Owner | Mitigation Strategy | Contingency Plan | Status | Date Identified | Last Updated
R001 | Scope | Scope creep due to unclear requirements | High | Medium | 12 | High | Project Manager | Implement formal change control process with approval workflow | Freeze scope after design sign-off | Mitigated | 2024-01-15 | 2024-02-10
R002 | Resources | Key developer resignation during critical phase | High | Low | 6 | Medium | Resource Manager | Cross-training and comprehensive documentation | Maintain relationships with contracting agencies | Monitored | 2024-01-15 | 2024-02-10
R003 | Technical | Integration challenges with legacy ERP system | High | High | 16 | Critical | Solution Architect | Build API abstraction layer and conduct early integration tests | Develop manual workaround procedures | Active | 2024-01-20 | 2024-03-01
R004 | Technical | Database performance degradation under load | High | Medium | 12 | High | Database Administrator | Implement caching and optimize queries during development | Horizontal scaling capability built-in | Active | 2024-02-01 | 2024-02-28
R005 | Schedule | Third-party vendor API delays | Medium | High | 12 | High | Project Manager | Early engagement with vendors and parallel development tracks | Identify alternative vendors | Active | 2024-01-25 | 2024-02-20
R006 | Budget | Infrastructure costs exceed estimates | Medium | Medium | 8 | Medium | Finance Manager | Monthly cost review and cloud resource optimization | Reserve 15% contingency budget | Monitored | 2024-01-15 | 2024-02-15
R007 | Stakeholder | Low user adoption post-deployment | High | High | 16 | Critical | Change Manager | Comprehensive training program and stakeholder engagement | Extended hypercare period and incentive program | Planned | 2024-02-05 | 2024-02-05
R008 | Security | Data breach during migration phase | Critical | Low | 9 | High | Security Officer | Encryption in transit and at rest plus access controls | Incident response plan and insurance | Mitigated | 2024-01-18 | 2024-02-12
R009 | Quality | UAT feedback requires major architectural changes | High | Medium | 12 | High | Business Analyst | Iterative UAT during development sprints | Phased rollout with MVP approach | Active | 2024-02-10 | 2024-02-28
R010 | Compliance | Regulatory requirements change during development | High | Low | 6 | Medium | Compliance Officer | Monthly regulatory monitoring and flexible architecture | Legal consultation and change request process | Monitored | 2024-01-22 | 2024-02-05
R011 | Technical | Mobile responsiveness issues on older devices | Medium | Medium | 8 | Medium | Frontend Developer | Progressive enhancement and device testing matrix | Graceful degradation for unsupported browsers | Planned | 2024-02-15 | 2024-02-15
R012 | Communication | Misalignment between technical and business teams | Medium | High | 12 | High | Project Manager | Weekly alignment meetings and shared documentation platform | Escalation path to steering committee | Mitigated | 2024-01-15 | 2024-02-25
R013 | External | Cloud provider outage during go-live | High | Low | 6 | Medium | DevOps Engineer | Multi-region deployment and backup data center | Rollback procedure and communication plan | Planned | 2024-02-01 | 2024-02-01
R014 | Schedule | Testing phase overruns due to high defect count | Medium | High | 12 | High | QA Manager | Test-driven development and continuous integration | Reduce scope or extend timeline | Active | 2024-02-08 | 2024-03-01
R015 | Resources | Budget cuts force resource reduction | High | Low | 6 | Medium | Project Manager | Prioritize critical path activities and automate | Renegotiate timeline with sponsors | Monitored | 2024-01-15 | 2024-01-30

## Risk Matrix
RISK MATRIX (Impact × Probability)
| Low Probability | Medium Probability | High Probability
Critical Impact | Medium | High | Critical
High Impact | Low | Medium | High
Medium Impact | Low | Medium | Medium
Low Impact | Low | Low | Medium

## Risk Summary
RISK SUMMARY DASHBOARD
Risk Category | Count | % of Total | Highest Severity
Technical | 4 | 27% | Critical
Resources | 2 | 13% | Medium
Schedule | 2 | 13% | High
Scope | 1 | 7% | High
Budget | 1 | 7% | Medium
Stakeholder | 1 | 7% | Critical
Security | 1 | 7% | High
Quality | 1 | 7% | High
Compliance | 1 | 7% | Medium
Communication | 1 | 7% | High
External | 1 | 7% | Medium
Status Breakdown
Active | 6 | 40% | Requires monitoring
Mitigated | 3 | 20% | Under control
Monitored | 4 | 27% | Watching closely
Planned | 2 | 13% | Future risks