## WBS Tasks
WBS ID | Task Name | Description | Owner | Duration (Days) | Dependencies | Start Date | End Date | Status | % Complete | Notes
1.0 | Project Initiation | Establish project foundation and governance | Project Manager | 10 |  | 2024-01-15 | 2024-01-26 | Complete | 100 | Foundation phase
1.1 | Project Charter Development | Define scope, objectives and success criteria | Project Manager | 3 |  | 2024-01-15 | 2024-01-17 | Complete | 100 | Approved by steering committee
1.2 | Stakeholder Identification | Map all stakeholders and their influence | Business Analyst | 2 | 1.1 | 2024-01-18 | 2024-01-19 | Complete | 100 | 25 stakeholders identified
1.3 | Team Formation | Recruit and onboard project team | Resource Manager | 5 | 1.1 | 2024-01-15 | 2024-01-22 | Complete | 100 | Core team of 8 assembled
2.0 | Requirements & Planning | Gather and document all requirements | Business Analyst | 15 | 1.0 | 2024-01-29 | 2024-02-16 | Complete | 100 | Requirements baseline locked
2.1 | Requirements Gathering | Conduct workshops and interviews | Business Analyst | 8 | 1.2 | 2024-01-29 | 2024-02-07 | Complete | 100 | 120 requirements documented
2.2 | Requirements Analysis | Validate and prioritize requirements | Solution Architect | 4 | 2.1 | 2024-02-08 | 2024-02-13 | Complete | 100 | MoSCoW prioritization applied
2.3 | Project Plan Creation | Develop detailed project schedule | Project Manager | 3 | 2.2 | 2024-02-14 | 2024-02-16 | Complete | 100 | MS Project baseline created
3.0 | Design Phase | Create technical and functional designs | Solution Architect | 18 | 2.0 | 2024-02-19 | 2024-03-14 | In Progress | 75 | Architecture review completed
3.1 | Architecture Design | Define system architecture and components | Solution Architect | 6 | 2.2 | 2024-02-19 | 2024-02-26 | Complete | 100 | Cloud-native microservices
3.2 | Database Design | Design data models and schemas | Database Administrator | 5 | 3.1 | 2024-02-27 | 2024-03-05 | Complete | 100 | PostgreSQL with Redis cache
3.3 | UI/UX Design | Create wireframes and mockups | UX Designer | 7 | 2.1 | 2024-02-19 | 2024-02-29 | In Progress | 70 | Figma prototypes for 12 screens
4.0 | Development | Build and integrate system components | Lead Developer | 28 | 3.0 | 2024-03-15 | 2024-04-23 | In Progress | 45 | Sprint 3 of 6 complete
4.1 | Backend Development | Develop APIs and business logic | Lead Developer | 15 | 3.1, 3.2 | 2024-03-15 | 2024-04-02 | In Progress | 60 | Node.js with Express
4.2 | Frontend Development | Build user interfaces | Frontend Developer | 15 | 3.3 | 2024-03-18 | 2024-04-05 | In Progress | 40 | React with TypeScript
4.3 | Database Implementation | Create database and seed data | Database Administrator | 8 | 3.2 | 2024-03-15 | 2024-03-26 | Complete | 100 | Migration scripts automated
4.4 | Integration | Connect frontend, backend and services | Integration Specialist | 10 | 4.1, 4.2 | 2024-04-03 | 2024-04-16 | Not Started | 0 | RESTful APIs planned
5.0 | Testing | Validate system functionality and performance | QA Manager | 14 | 4.0 | 2024-04-24 | 2024-05-13 | Not Started | 0 | Test plan approved
5.1 | Unit Testing | Test individual components | QA Engineer | 8 | 4.1, 4.2 | 2024-04-24 | 2024-05-03 | Not Started | 0 | Jest and React Testing Library
5.2 | Integration Testing | Test component interactions | QA Engineer | 6 | 4.4 | 2024-05-04 | 2024-05-11 | Not Started | 0 | Automated test suites
5.3 | User Acceptance Testing | Validate with end users | Business Analyst | 10 | 5.2 | 2024-05-12 | 2024-05-25 | Not Started | 0 | 20 pilot users identified
5.4 | Performance Testing | Load and stress testing | Performance Engineer | 5 | 5.2 | 2024-05-06 | 2024-05-12 | Not Started | 0 | 1000 concurrent users target
6.0 | Deployment | Deploy to production environment | DevOps Engineer | 7 | 5.0 | 2024-05-26 | 2024-06-03 | Not Started | 0 | Blue-green deployment
6.1 | Environment Setup | Configure production infrastructure | DevOps Engineer | 3 | 5.2 | 2024-05-26 | 2024-05-28 | Not Started | 0 | AWS EC2 and RDS
6.2 | Data Migration | Migrate data from legacy system | Database Administrator | 4 | 6.1 | 2024-05-29 | 2024-06-01 | Not Started | 0 | ETL pipeline with validation
6.3 | Go-Live | Production deployment and monitoring | Project Manager | 2 | 6.2 | 2024-06-02 | 2024-06-03 | Not Started | 0 | War room activated
7.0 | Post-Deployment | Support and optimization | Support Team | 10 | 6.0 | 2024-06-04 | 2024-06-17 | Not Started | 0 | Hypercare period
7.1 | User Training | Train end users on new system | Training Specialist | 5 | 6.3 | 2024-06-04 | 2024-06-10 | Not Started | 0 | Live and recorded sessions
7.2 | Hypercare Support | Intensive support period | Support Team | 10 | 6.3 | 2024-06-04 | 2024-06-17 | Not Started | 0 | 24/7 support desk
7.3 | Project Closure | Document lessons learned | Project Manager | 3 | 7.2 | 2024-06-18 | 2024-06-20 | Not Started | 0 | Final report to steering

## Project Summary
PROJECT SUMMARY DASHBOARD
Metric | Value | Status | Notes
Total Tasks | 30 | 100% | All tasks defined
Completed Tasks | 15 | 50% | 15 of 30 complete
In Progress Tasks | 4 | 13% | Currently active
Not Started Tasks | 11 | 37% | Upcoming work
Overall Progress | 45% | On Track | Week 8 of 12
Budget Status | $175K / $250K | Under Budget | $5K variance
Schedule Status | Week 8 | On Track | No delays
Risk Status | 5 Active | Manageable | 2 high priority